## Foundational Setup
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort | status
T1.1 | Set up Cloudflare R2 bucket and API credentials | Create an R2 bucket in Cloudflare. Obtain your Cloudflare Account ID, R2 Access Key ID, and R2 Secret Access Key. Crucially, store these credentials securely (e.g., as environment variables in your system profile, or in a .env file that is NOT committed to version control). | Manual Setup / Cloud Provisioning | Yes | Cloudflare Account, Web Browser | R2 bucket created; all necessary credentials obtained and securely stored. |  | Medium
T1.2 | Install Docker & Docker Compose | Install Docker Desktop (for Windows/macOS) or Docker Engine and Docker Compose (for Linux). Ensure the Docker daemon is running and configured to start on boot. | Manual Setup / Local Environment | Yes | Operating System Access, Internet | Docker and Docker Compose are installed and running correctly. `docker --version` and `docker-compose --version` execute successfully. |  | Medium
T1.3 | Set up PostgreSQL database via Docker | Pull the PostgreSQL Docker image. Run a container, configuring the database name (`mf_db`), user (`mf_user`), password (`your_secure_password`), and port mapping (`-p 5432:5432`). Ensure it starts automatically with Docker. Store these credentials securely. | Local Environment Setup / Docker | No | Docker, PostgreSQL Docker Image | PostgreSQL container is running and accessible (e.g., via `psql` from host). Database, user, and password are set. | T1.2 | Medium
T1.4 | Install Python and set up virtual environment (using uv) | Install Python (version 3.9 or higher is recommended). Install uv globally or via a standalone binary. Create a virtual environment for your project using uv (uv venv). Activate it (source venv/bin/activate on Linux/macOS, .\venv\Scripts\activate on Windows Powershell). | Manual Setup / Local Environment | Yes | Python Installer, Terminal, uv | Python installed, uv installed, virtual environment created and activated. uv --version shows installed version. | - | Low
T1.5 | Install Apache Spark & PySpark (local mode) | Download Apache Spark binaries (e.g., spark-3.5.1-bin-hadoop3.tgz). Extract them. Set the SPARK_HOME environment variable to the extracted directory. Add SPARK_HOME/bin to your system's PATH. Install pyspark using uv (uv pip install pyspark). Download the PostgreSQL JDBC driver (postgresql-.jar) and place it in Spark's jars directory ($SPARK_HOME/jars/). | Manual Setup / Local Environment | Yes | Apache Spark Binaries, JDK, Terminal, uv | pyspark command launches Spark shell. PySpark installed in virtual environment. JDBC driver accessible to Spark. | T1.4 | High
T1.6 | Install Prefect library and set up Prefect Cloud account | Install Prefect Python library using uv (uv pip install prefect). Create an account on Prefect Cloud (https://cloud.prefect.io/). Generate a Prefect API key from the UI. Configure Prefect CLI to connect to Prefect Cloud (prefect cloud login). | Manual Setup / Cloud Configuration | Yes | Web Browser, Terminal, uv | Prefect installed. Prefect Cloud account active. prefect cloud login successful. Prefect API key obtained. | T1.4 | Medium
T1.7 | Initialize Project Structure & Dependencies | Create the specified project directory structure. Generate the .gitignore file. Prepare the initial requirements.txt with base dependencies. Instruct the human user to manually create and populate the .env file with sensitive credentials. | Code Generation / File System Operation | No | Terminal, File System Access | Project directory structure is created. .gitignore is correct. requirements.txt has base deps installed. Human user is prompted for .env creation. | T1.4, T1.5, T1.6 | High

## Raw Data Ingestion Layer
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort
T2.1 | Confirm Zerodha Coin API endpoint & authentication method | Consult Zerodha Coin API documentation to confirm the exact endpoint URL for MF instrument dump and the precise authentication headers/parameters required (e.g., API key in `Authorization` header). Obtain your actual Zerodha API key. | Manual Research / Credential | Yes | Web Browser, Zerodha Account | API endpoint URL and authentication method confirmed. Required API key obtained. |  | Medium
T2.2 | Develop Python script to fetch Weekly MF Instrument Dump from Zerodha | Write a Python script (`fetch_zerodha_instruments.py`) that uses the `requests` library to make an API call to Zerodha (using details from `T2.1`). Parse the CSV response (`pandas.read_csv(io.StringIO(response.text))`). Save the DataFrame as a CSV file to your R2 bucket (`T1.1`) using `boto3` or `s3fs`, following the `YYYY/MM/DD/filename_timestamp.csv` naming convention. Implement basic logging, error handling (`try-except`), and retries for API calls. | Code Development / Script Exec. | No | Python, `requests`, `boto3`/`s3fs` | Script runs successfully, fetches data, and saves a properly named CSV file to R2. Logs show success/failure. | T1.1, T1.4, T2.1 | Medium
T2.3 | Define process for landing Daily AMFI NAV data to R2 | Outline the method for your existing AMFI scraping process to save its output (assumed CSVs, either one file per instrument or one daily consolidated file) directly to the designated R2 path (`YYYY/MM/DD/nav_daily_YYYYMMDD.csv` or `nav_ISIN_YYYYMMDD.csv`). This will typically involve modifying your existing scraper to use `boto3` or `s3fs` to write to `r2://your-bucket/raw/amfi_nav_daily/YYYY/MM/DD/nav_daily_YYYYMMDD.csv` (or similar). Ensure consistent naming and directory structure. | Process Definition / Script Adapt. | No | Existing AMFI Scraper, Python, `boto3`/`s3fs` | AMFI data successfully moved/written to R2 with correct naming convention. Data is accessible in R2. | T1.1, T1.4 | Low

## Data Transformation
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort
T3.1 | Define and create `dim_mutual_fund` table DDL in PostgreSQL | Write the SQL Data Definition Language (DDL) script to create the `dim_mutual_fund` table in PostgreSQL. Columns to include: `fund_key` (BIGSERIAL PRIMARY KEY), `current_isin` (TEXT), `amc` (TEXT), `name` (TEXT), `plan` (TEXT), `dividend_type` (TEXT), `start_date` (DATE), `end_date` (DATE, NULLABLE), `is_current` (BOOLEAN), `data_source` (TEXT), `ingestion_timestamp` (TIMESTAMP). Indexing: Create indices on `(amc, name, plan, dividend_type)` (the natural key for efficient lookup during SCD2 processing), and on `current_isin` (for joining with NAV data), and `is_current`. | SQL Development / DB Schema | No | SQL Client (e.g., psql) | Table `dim_mutual_fund` created in PostgreSQL with correct schema and indices. Natural key columns are suitable for normalized values. | T1.3 | Medium
T3.2 | Develop PySpark script for Weekly MF Instrument SCD Type 2 processing | Write a PySpark script (`process_mf_instruments.py`) that performs the SCD Type 2 logic for `dim_mutual_fund`. 1. **Read Inputs:** Load the latest raw `mf_instruments.csv` from R2 (`T2.2`) and the entire `dim_mutual_fund` table from PostgreSQL (`T3.1`). 2. **Clean Natural Key:** Apply consistent data cleaning (lowercase, strip whitespace, normalize internal whitespace) to `amc`, `name`, `plan`, and `dividend_type` in *both* the incoming data and the existing dimension data for accurate matching. 3. **Identify Changes:** Perform joins/comparisons using the cleaned natural key to identify: - **New Funds:** Insert new records into `dim_mutual_fund` (`start_date=current, end_date=NULL, is_current=TRUE`). - **Changed Funds:** For logical funds whose `current_isin` has changed: `UPDATE` the old `is_current=TRUE` record (`set end_date=yesterday, is_current=FALSE`); then `INSERT` a new record (`start_date=current, end_date=NULL, is_current=TRUE`) with the new ISIN and a new `fund_key`. - **Deactivated Funds:** `UPDATE` records in `dim_mutual_fund` that are `is_current=TRUE` but no longer appear in the incoming dump (`set end_date=yesterday, is_current=FALSE`). 4. **Write Back:** Orchestrate these `UPDATE` and `INSERT` operations to `dim_mutual_fund` in PostgreSQL (e.g., using a staging table and `MERGE`-like logic, or direct updates/inserts). | Code Development / PySpark | No | PySpark, PostgreSQL JDBC, R2 access | Script runs successfully, correctly identifies all change scenarios, and updates `dim_mutual_fund` adhering to SCD2 principles. | T1.5, T2.2, T3.1 | High
T3.3 | Implement Data Cleaning & Sanity Checks for Raw NAV data in PySpark | Enhance your PySpark script (likely `process_daily_navs.py`) to apply data cleaning and sanity checks immediately after reading raw NAV data from R2 (`T2.3`). Checks include: Data type validation (`nav_date` to DATE, `nav_value` to NUMERIC), handling missing critical values (discard/quarantine if critical), duplicate check on `(source_isin, nav_date)`, `nav_value` range/positivity check. Implement logging for all validation outcomes. Error Handling: Define clear logic for valid data vs. quarantined data vs. discarded data. | Code Development / PySpark | No | PySpark, R2 access | Script correctly cleans and validates NAV data. Bad data is either discarded with clear logs or moved to a designated quarantine location (e.g., a separate R2 path or PostgreSQL table). | T1.5, T2.3 | Medium
T3.4 | Define and create `fact_nav_daily` table DDL in PostgreSQL | Write the SQL DDL script to create the `fact_nav_daily` table in PostgreSQL. Columns to include: `nav_key` (BIGSERIAL PRIMARY KEY), `fund_key` (BIGINT, FOREIGN KEY referencing `dim_mutual_fund`), `nav_date` (DATE), `nav_value` (NUMERIC), `source_isin` (TEXT), `ingestion_timestamp` (TIMESTAMP), `scrape_date` (DATE). Indexing: Create indices on `(fund_key, nav_date)` for efficient time-series queries. | SQL Development / DB Schema | No | SQL Client (e.g., psql) | Table `fact_nav_daily` created in PostgreSQL with correct schema and indices. Foreign Key constraint to `dim_mutual_fund` is defined. | T1.3, T3.1 | Medium
T3.5 | Develop PySpark script for Daily NAV data processing & loading | Write a PySpark script (`process_daily_navs.py`) that handles NAV processing and loading. 1. Reads the *cleaned* NAV data (output of `T3.3`). 2. Reads the *entire* `dim_mutual_fund` table (all historical versions) from PostgreSQL. 3. **Crucial Join:** Joins the NAV data with `dim_mutual_fund` on `daily_nav_df.source_isin = dim_mutual_fund.current_isin` AND `daily_nav_df.nav_date BETWEEN dim_mutual_fund.start_date AND COALESCE(dim_mutual_fund.end_date, '9999-12-31')` to retrieve the correct `fund_key` for each NAV record. 4. Handles unmatched NAVs (log/quarantine). 5. Appends the processed DataFrame to `fact_nav_daily` in PostgreSQL. Implement idempotency (avoiding duplicates on re-runs) based on `(fund_key, nav_date)`. | Code Development / PySpark | No | PySpark, PostgreSQL JDBC, R2 access | Script runs successfully, links NAVs to the correct `fund_key`s from `dim_mutual_fund`, and appends data to `fact_nav_daily` table without duplicates. | T1.5, T3.1, T3.3, T3.4 | High
T3.6 | Build 'Simple App' for Human-in-the-Loop Natural Key Validation | Develop a Python script (can be CLI-based, or use Streamlit/Dash for a simple web UI) that: 1. Queries/reads `NEEDS_REVIEW` cases identified by T3.2's heuristic. 2. Presents relevant details of incoming and potential matching `dim_mutual_fund` records. 3. Allows the user to manually classify each case (e.g., 'new fund', 'change to fund_key X', 'discard'). 4. Stores these manual decisions in a structured format (e.g., a small PostgreSQL table or a CSV file in R2) that T3.2 can read and apply as overrides. | Code Development / UI | Yes | Python, SQL Client (or Streamlit) | App runs, displays review items, accepts user input, and stores decisions in a structured format accessible by T3.2 for final processing. | T1.4, T3.2 | High

## Orchestration
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort
T4.1 | Create Prefect Flow for Weekly Instrument Ingestion & Transformation | Define a Prefect flow (`weekly_instrument_flow.py`) that orchestrates the weekly pipeline. Flow steps: 1. Task to execute T2.2 (fetch Zerodha data). 2. Task to execute T3.2 (process SCD2 for `dim_mutual_fund`, including initial heuristic matching). 3. **Manual Approval Task:** Integrate a Prefect `manual_check` task that pauses the flow after T3.2's initial heuristic pass, pending review and decision from T3.6. 4. Task to re-execute the final part of T3.2 (applying manual decisions and final updates to `dim_mutual_fund`). Execution Context: Ensure environment variables for R2/DB credentials are passed to the tasks. | Code Development / Orchestration | No | Prefect, Python | Prefect flow definition is valid and successfully registers with Prefect Cloud. Tasks are correctly linked, including manual intervention point. | T1.6, T2.2, T3.2, T3.6 | Medium
T4.2 | Create Prefect Flow for Daily NAV Ingestion & Transformation | Define a Prefect flow for the daily NAV pipeline. Flow steps: 1. Task to ensure raw NAV data is landed in R2 (can be a dummy task if T2.3 is external, or a Prefect task that runs the landing script). 2. Task to execute T3.3 (clean NAV data). 3. Task to execute T3.5 (process & load NAV data to `fact_nav_daily`). Dependencies: Ensure this flow can be configured to run daily. Consider adding an optional dependency on T4.1 to ensure `dim_mutual_fund` is up-to-date before processing NAVs if a specific weekly run just completed. | Code Development / Orchestration | No | Prefect, Python | Prefect flow definition is valid and successfully registers with Prefect Cloud. Tasks are correctly linked. | T1.6, T2.3, T3.3, T3.5 | Medium
T4.3 | Configure Prefect Agent to run pipeline | Start the Prefect Agent on your local machine (or a small cloud VM if you prefer an "always-on" environment). The agent polls Prefect Cloud for scheduled or manually triggered flow runs and executes them. This agent will need access to your Python environment, PySpark installation, and relevant credentials. | Agent Setup / Runtime | Yes | Terminal, Prefect CLI, Docker (optional) | Prefect Agent is running and successfully connected to Prefect Cloud. It can pick up and execute simple test flows. | T1.6, T4.1, T4.2 | Low
T4.4 | Set up scheduling for Prefect Flows | Within the Prefect Cloud UI, configure the weekly schedule for `weekly_instrument_flow` (`T4.1`) and the daily schedule for `daily_nav_flow` (`T4.2`). Confirm that the schedules are active and show upcoming runs. | Cloud Service Configuration | Yes | Web Browser, Prefect Cloud UI | Flows are correctly scheduled in Prefect Cloud and appear in the "Upcoming Runs" section. | T4.1, T4.2, T4.3 | Low

## Data Serving
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort
T5.1 | Connect BI tool (e.g., Metabase) to PostgreSQL | Install and configure a BI tool of your choice (e.g., Metabase, which can run as a Docker container, or another tool). Establish a connection to your PostgreSQL database (`T1.3`) using the provided credentials. Verify the connection by navigating the database schema and running simple queries against the `dim_mutual_fund` (`T3.1`) and `fact_nav_daily` (`T3.4`) tables. Create a basic dashboard to confirm data visibility. | Tool Setup / Configuration | Yes | BI Tool (Metabase/Others), Docker (opt) | BI tool successfully connects to PostgreSQL, lists the tables, and can display data from `dim_mutual_fund` and `fact_nav_daily`. | T1.3, T3.1, T3.4 | Medium
T5.2 | Develop core queries/data access for Simulation Tool | Write the Python code within your simulation application to connect to the PostgreSQL database using the `psycopg2` library. Develop efficient SQL queries to fetch relevant time-series and dimension data (e.g., NAV history for a specific `fund_key`s over a given date range). Optimize queries using indices defined in PostgreSQL. | Code Development / App Integr. | No | Python, `psycopg2`, Code Editor | Simulation tool can programmatically fetch data required for its operations efficiently from PostgreSQL. Queries are optimized to fetch only necessary data. | T1.4, T1.3, T3.1, T3.4 | High
T5.3 | Create common analytical views in PostgreSQL (optional) | Develop SQL views in PostgreSQL to pre-aggregate commonly used metrics (e.g., monthly average NAV, fund returns), simplify complex joins between `dim_mutual_fund` and `fact_nav_daily`, or create summarized tables. This can make reporting faster and easier for BI users who might not be proficient in complex SQL. These views can also be materialized views if the data needs to be frequently queried but updated less often. | SQL Development / Optim. | No | SQL Client, PostgreSQL | Required analytical views are created in PostgreSQL. Views provide simplified access to aggregated or joined data. | T1.3, T3.1, T3.4 | Medium

## QA & Monitoring
Task ID | Name | Description | Type | Human Intervention Required | Required Tools | Success Criteria | Dependencies | Estimated Effort
T6.1 | Implement comprehensive logging within all Python/PySpark scripts | Integrate Python's `logging` module effectively into all your ingestion (`T2.2`, `T2.3`) and transformation (`T3.2`, `T3.3`, `T3.5`) scripts. Log crucial events (start/end of tasks), warnings, errors (with stack traces), processed row counts, and detailed information about data quality issues (e.g., which rows were discarded or quarantined). Ensure logs are informative enough for debugging. | Code Development / Observability | No | Python `logging`, PySpark, Code Editor | Scripts produce structured, informative logs that are captured by Prefect and aid debugging. | T2.2, T2.3, T3.2, T3.3, T3.5 | Medium
T6.2 | Set up Prefect Cloud monitoring and alerts | Within the Prefect Cloud UI, configure dashboards to monitor your flow runs (T4.1, T4.2). Set up automated alerts (e.g., email or Slack notifications if you integrate with them) for critical events like flow failures, task failures, or tasks that run significantly longer than expected. Test these alerts by simulating a flow failure. | Cloud Service Configuration | Yes | Web Browser, Prefect Cloud UI | Monitoring dashboards are active and show flow/task status. Notifications are received promptly upon simulated flow failures. | T4.4 | Low
T6.3 | Develop basic data quality checks post-load in PostgreSQL | Write SQL queries or a simple Python script (using `psycopg2` or `SQLAlchemy`) that runs daily/weekly after data load. These checks will verify data integrity and quality in your PostgreSQL tables. Examples: - No negative `nav_value` in `fact_nav_daily`.- No duplicate `(fund_key, nav_date)` pairs in `fact_nav_daily`.- Count of `is_current=TRUE` records in `dim_mutual_fund` matches expectations.- Basic aggregate checks (e.g., sum of NAVs for a month is within a reasonable range). If anomalies are found, log them or trigger alerts. | Code Development / Data Quality | No | SQL Client, PostgreSQL, Python (opt) | Data quality checks run as scheduled and identify any defined anomalies. Results are logged or can be easily reviewed. | T3.5 | Medium
T6.4 | Document key architectural decisions and code | Maintain a running document (e.g., Markdown files in your GitHub repository's `docs/` folder or a wiki) that details: - The overall architecture. - Key technology choices and their rationale. - Setup steps for the environment. - Detailed logic for SCD Type 2 and data cleaning. - Troubleshooting notes. This documentation is crucial for maintenance and future reference. | Documentation | Yes | Text Editor / Markdown, GitHub Repo | Comprehensive documentation exists for all major components and decisions. |  | Ongoing